CVH Opening Event Day – 9 May 2026

Planning Document – master

| Date | Discussion Point | Agreed Action | Owner | Status |
| --- | --- | --- | --- | --- |
| 030326 | Event | CVH – Opening Event | Committee |  |
|  | Date | 09 May 2026 | Committee |  |
| 090326 | Lord Lieutenant of Fife | Confirmed for 1pm Event start time. Contact: Lynda Birrell Fife.Lieutenancy@fife.gov.uk L Birrell ¦ Clerk to the Lord-Lieutenant of Fife Lieutenancy of Fife ¦ Fife House ¦ GLENROTHES ¦ Fife ¦ KY7 5LT Tel: 03451 555555 ext 440336 ** Of note – Dietary – Gluten Free** | KM |  |
| 09/03/2026 | Timeline of Event | 13.00 Arrival and commence event Bagpipe welcome? Serve alcohol/non alcohol toast Canapes/small bite food 13.15 Lord Lieutenant Section 13.20 Speech – inside 13.30 Plant Tree outside 13.45 Cake cutting inside 13.50 Thank you to community support and Funders - Chair/Vice Chair 14.30 Wind up and usher to anti-area? 14.45 Set up Tables inside large room 15.00 Phase 2 Commence Community Open Afternoon/Social BYOB and food. 1600 Music Section – local group – tbc? Social afternoon. 1900 CLOSE | Committee agreed 10/03/2026 |  |
| 090326 | Guest List | AM collated initial list of names and Circa 50 initial names including Funders/VIP/Committee – past and present. Key community persons that need invited also. - Provisional 100 maximum in hall - Agreed that all Community need to be invited – circa 180 households. - unlikely all will attend based on previous engagement. - AM to start with VIP/Committee members and funders and any persons that need email invite. - NM created email address for RSVP. - RSVP_2026CVH@outlook.com AM will issue invites week commencing 16/03/2026. - Remaining households will receive printed card by delivery circa –early April – RSVP for 15th April 2026. | AM |  |
|  | Invites | Design/Print and prepare - SM has Vistaprint format for “card Invite” - Use this format and agreed font and colours at meeting of 10/03/2026. - Adding “Invitation” to the front of card – dark side. - RVSP details to be added and outline of times. - AM emailed to SM for initial draft at Vista Print. | SM/AM |  |
|  | Wording on invite | Agreed by Committee to be as inclusive as possible: “You are invited to the Grand Re-Opening of the Village Hall on 9th May 2026. Please arrive for 1pm when the Lord-Lieutenant of Fife will perform the ceremonial opening on behalf of the Community at 1.15pm.” | Committee Agreed 10/03/2026 | ALL |
|  | Parking | Lord Lieutenant asked for space – 1 space. Disabled Parking only – mininal access. Drop off – will need managed on the day especially if people outside for tree planting. |  |  |
|  | Teas/Coffees/ Food/Alcohol Initial discussion | Budget – discussed options – no set figure but as cost efficient as possible. - Agreed 1 glass fizz – can be topped up. - Committee will pour for arrival. - Soft drinks alternative. - Small bites – easy foods – with minimal preparation involved and no heated food. - Cake – large - to be ordered with CVH logo and colours which can be cut and shared out. - Diatery options – Gluten free – consider – small cake option? | Agreed by Committee 10/03/2026 |  |
|  | Cake | Initial enquiry to ARH – for lady in Chance Inn | SM |  |
|  | Crockery | Disposable and Recycable – as far as possible | FG |  |
|  | Room set up | Phase 1 Agreed – seating for circa 20 – but main room will be open space with tables at side for drinks/food etc initially to create social space – not too formal Phase 2 Usher guests out to allow for Tables and chairs to be set up for attendees. | ALL |  |
|  | Stage? | Suggestion if there is a raised area – school previously loaned – low platform. |  |  |
|  | Speech prepare | Speech 1 Note will need to be sent to the Lord Lieutenant. Speech 2 Community thanks on behalf of Committee and to funders support also. | Chair/Vice Chair |  |
|  | Dress Code | Protocol – Smart Day wear for Lord Lieutenant Wearing Neck Ribbon | ALL |  |
|  | Plaque | Order- do we still want this inside? |  |  |
|  | Tree | Order and discussion about type. Fruit or flowering tree for community presence |  |  |
|  | Licences for Alcohol | Fife Council checks | KM |  |
|  | Entertainment Licence | Fife Council checks | KM |  |
|  | Gazebo | MW and JW said they have one that could be used if raining | MW/JW |  |
|  | Bagpipes | SW checking contact – for arrival event | SW |  |
|  | School involvement | Check how involved school want to be as it is a Saturday. Email head teacher and check with ARH – for thoughts. SW/WJ have now spoken with teacher as has ARH and school wish to be involved. | WJ AM |  |
|  | Press and communcation | The Courier/Fife Herald Contact with information and dates | AM |  |
|  | Photography | Press and NM/SM? | NM/SM |  |
|  | Commerative keep sake | Book Mark suggested by PG – samples looked at and agreed good idea. Possible Vista Print option – costs not prohibitive | SM/PG |  |
| Phase 2 – Afternoon/Early Evening |  |  |  |  |
|  |  | Check if Fiona and John Drysdale can support the event – circa 4- 5pm? | AM/KM |  |
|  |  | BYOB agreed by committee and not bar. |  |  |
|  |  | Press |  |  |
|  |  | Attendees – Numbers and Register |  |  |
| Roles |  |  |  |  |